| Objectives, Metrics and Projects |
| --- |
| Objective 4.1 |
| Develop a self-sustaining Hub program. |
| Metrics |
| Completion of Hub Program Management Plan Identify Hub sites throughout city Standardization of a Hub kit & purchase of needed supplies Develop and deliver a Hub training and exercise program | Completion of Hub protocols and procedures Recruit and engage personnel from the community into the Hub program Recruit and engage the community at large to support the Hub program Incorporate hubs into the EOC and ERP |
| Existing Projects | Status |
| 1. Identifying libraries as Hub sites and training of library staff 2. Completion of a Hub exercise for several library sites 3. Developing Hub staff procedures, including a communication plan 4. Identify funding source & purchase necessary supplies and equipment 5. Complete and implement the Hub Management Plan 6. Incorporate Hubs into Community Branch Annex | 1. In progress 2. Projected completion: October 15, 2009 3. Job action sheets are completed 4. Pending funding 5. Plan completed; implementation in progress 6. On-going |
| New Projects | Status |
| 1. 2. 3. 4. |  |

| Objectives, Metrics and Projects |
| --- |
| Objective 4.2 |
| Support increased resiliency for nonprofits and faith-based organizations |
| Metrics |
| Develop Continuity of Operations Template that meets the needs of the NGO community Develop standards for NGOs that will facilitate the development and sustainment of disaster resilient activities |
| Existing Projects | Status |
| 1. NGO Continuity of Operations Template 2. NGO Standards development 3. | 1. Underway in partnership with Bay Prep collaborative & California Volunteers 2. Underway in partnership with Bay Prep collaborative |
| New Projects | Status |
| 1. Work with funders to support implementation of NGO Standards 2. 3. 4. |  |

| Objectives, Metrics and Projects |
| --- |
| Objective 4.3 |
| Improve coordination with NGOs in a disaster and among NGO service providers. |
| Metrics |
| Develop MOU for use of Bay Area Coordinated Assistance Network (BA CAN) in Care & Shelter DOC and EOC Clarify NGO coordination role in Emergency Operations Center Hold quarterly seminars for NGO community in partnership with Bay Prep |
| Existing Projects | Status |
| 1. Develop protocols and activation toolkit for Bay Area CAN 2. Participate on SF CARD (Community Agencies Responding in Disasters) Executive and Steering Committees | 1. In progress |
| New Projects | Status |
| 1. 2. |  |

| Objectives, Metrics and Projects |
| --- |
| Objective 4.4 |
| Engage the public about potential risks and promote all-hazard emergency preparedness activities as a daily responsibility of all San Franciscans |
| Metrics |
| Conduct annual Shake Out Exercise Participate in annual Big Rumble events Maintain innovative websites to provide information about preparedness Conduct outreach activities related to 72hours.org Develop neighborhood focused outreach efforts |
| Existing Projects | Status |
| 1. Big Rumble 2009 2. Shake Out 2009 3.Promote customizable 72hours.org website to other jurisdictions 4. Develop Map Your Block (MYB) program 5. Quarterly brochure distributions to DPH Clinics | 1. in progress 2. in progress 3. 72hours.org/anywhere CMS near completion 4. in progress 5. On-going |
| New Projects | Status |
| 1. Develop online tool as companion to MYB brochure 2. Make improvements to QuakeQuiz SF by incorporating sound and developing Spanish language version |  |

| Objectives, Metrics and Projects |
| --- |
| Objective 4.5 |
| Build effective partnerships to support outreach and preparedness efforts |
| Metrics |
| Use on-line tools to improve information sharing Increase Citizen Corps Council participation by private sector and City Departments |
| Existing Projects | Status |
| 1. SF Citizen Corps Council website 2. Coordination with Statewide Citizen Corps Council 3. | 1. |
| New Projects | Status |
| 1. 2. 3. |  |

| Objectives, Metrics and Projects |
| --- |
| Objective 4.6 |
| Support the resiliency of all educational institutions in San Francisco. |
| Metrics |
| Complete the SFUSD EOP Provide a Site Template Plan to all SF Schools. Provide Personal Preparedness to the schools. Conduct TTX exercises with all levels of schools Include schools, universities, and the private sector in disaster preparedness activities and emergency management. Engage Independent Schools in the emergency plans of the City |
| Existing Projects | Status |
| 1. Creation of Higher Education Council to collaborate and coordinate all emergency management and preparedness projects 2. Conduct ARC sponsored Minute Preparedness in the SFUSD High Schools 3. Student Emergency Response Volunteer Program 4. Development of the SFUSD EOP 5. Development of s SFUSD school site EOP template | 1. Monthly meetings are on-going with a TTX tentatively scheduled for September 2 Completed 3 Initial course design was proposed by DEM to the District and School Board, however its development is currently on hiatus 4. EOP will be reviewed and completed by September 1, 2009 5. School Site Template will be reviewed and completed by Sept 1, 2009 |
| New Projects | Status |
| 1. Convert SFUSD School Site EOP Template to be used by Independent schools in the Region |  |