Integrated HRIS Project

September 6, 2006

The following is a synopsis of deliverables expected from GFOA.  The deliverable sequence and dates are taken from the first draft project plan from GFOA and are subject to change as the project evolves.  Items shown in blue font are included in the GFOA contract; other items are key events or activities.

| Ref # | Major Activity or Deliverable | Due Date | Status |
| --- | --- | --- | --- |
| Phase I – Business Case Analysis/Requirements Development |  |  |
| 1.1 | Initial Kickoff meeting | July 25th | Completed |
| 1.2 | On-site visit #1 – requirements gathering | August 10th | Completed |
| 1.3 | First Draft Requirements | August 28th | Completed |
| Phase II – Requirements Definition |  |  |
| 2.1 | Draft Project Plan | August 23th | Completed |
| 2.2 | On-site visit #2 – requirements refining | September 14th | Planned |
| 2.3 | Synopsis of Critical HRMS Business Needs Report Draft | September 21st |  |
| 3.1 | Preliminary Business Requirements | September 21st |  |
| 3.2 | On-site visit #3 – requirements validation | September 29th |  |
| 4 | Validated Business Requirements | October 2nd |  |
| Phase IIA – Software System Selection |  |  |
| 5 | Software Evaluation Plan (draft and final) | October 5th October 16th |  |
| 6.1 | Business Requirements Analysis Report | October 25th |  |
| 6.2 | Vendor Demos 1-2-3 | November 16th |  |
| 6.3 | Elevate Finalist Software Vendor(s) | November 17th |  |
| 6.4 | Contract Negotiation (Software License Agreement) | December 18th |  |
| Phase III – Implementation Services RFP Development & Selection |  |  |
| 7.1 | On-site visit – gather development information | September 29th |  |
| 7.2 | Draft RFP Document | October 31st |  |
| 8 | Final RFP Document | November 15th |  |
| 9 | Final Proposal Evaluation Plan | November 23rd |  |
| 10 | Summary Proposal Analysis Report | January 18th |  |
| 11.1 | [Implementation]Vendor Interview Scripts | January 12th |  |
| 11.2 | Software Interview Evaluation Tool | January 23rd |  |
| 12 | Implementation Vendor References Report | February 7th |  |
| 13 | GFOA Facilitation of Vendor Interviews (3 vendors) | February 12th |  |
| Phase IV – Discovery and Contract Negotiations |  |  |
| 15 [sic] | Final Discovery Letters and Agenda | February 21st |  |
| 14 | Facilitation of Final Vendor Identification Session(s) | March 8th |  |
| 17 [sic] | GFOA makes Statement of Work to Finalist Vendor | March 13th |  |
| 16 | Analysis on Key Implementation Services Agreement Clauses | April 13th |  |